## Sheet1
Task Name | Start Date | End Date | Progress % | PIC | Category | Priority | Remarks
Project Kickoff | 2026-05-01 | 2026-05-03 | 100 | Alice | Planning | High | Initial alignment done
Requirements Gathering | 2026-05-04 | 2026-05-10 | 100 | Bob | Planning | High | Signed off by stakeholders
Design Phase | 2026-05-11 | 2026-05-20 | 80 | Charlie | Design | Medium | Waiting for client feedback
UI Review | 2026-05-18 | 2026-05-22 | 60 | Alice | Design | Low
Development Sprint 1 | 2026-05-21 | 2026-06-05 | 45 | Dave | Development | High | Blocked by API specs
Development Sprint 2 | 2026-06-06 | 2026-06-20 | 10 | Dave | Development | High
API Integration | 2026-06-10 | 2026-06-18 | 5 | Eve | Development | Medium | Pending access credentials
QA Testing | 2026-06-21 | 2026-06-28 | 0 | Frank | QA | High
UAT | 2026-06-25 | 2026-07-02 | 0 | Grace | QA | Medium | Schedule with client TBD
Deployment | 2026-07-03 | 2026-07-05 | 0 | Dave | DevOps | High
Project Closure | 2026-07-06 | 2026-07-10 | 0 | Alice | Planning | Low